WEEK 1 PROJECT PLANNING & REQUIREMENTS ANALYSIS

Smart Expense Tracker

A web-based personal finance management application

| Document Detail | Information |
| --- | --- |
| Project Type | Web-based software application |
| Prepared By | Junior Intern |
| Planning Phase | Week 1 — Project Planning and Requirements Analysis |
| Estimated Week 1 Effort | 32 hours |
| Planned Development Duration | 8 weeks |
| Target Users | Students, young professionals, and individual users |
| Document Version | 1.0 |

Internship / Training Submission

# 1. Project Overview

## 1.1 Project Background

Smart Expense Tracker is a fictional but realistic web application that helps individuals record income and expenses, organize spending into categories, set monthly budgets, and understand their financial habits through a simple dashboard. The project is designed as an MVP for students and young professionals who want a convenient way to maintain personal expense records without depending on spreadsheets.

## 1.2 Problem Statement

People often make small daily purchases but do not maintain a consistent record of them. As a result, it can be difficult to understand where money is being spent, whether a monthly budget is being followed, or which categories consume the most money. Existing financial applications can also contain features that are unnecessary for a beginner. The proposed system focuses on a simple, understandable experience for recording and reviewing personal finances.

## 1.3 Proposed Solution

The system will provide a secure account, transaction management, categories, budgets, search/filter options, and a visual dashboard. Users can add income and expenses, view their current balance, monitor category-wise spending, and receive alerts when spending approaches or exceeds a selected budget.

## 1.4 Target Users

| User Type | Needs | Main Activities |
| --- | --- | --- |
| Student | Track limited monthly spending | Record expenses, set budget, view reports |
| Young Professional | Monitor income and recurring expenses | Manage transactions, categories and monthly budget |
| Individual User | Understand personal spending habits | Review dashboard, filter transactions, export/report data |
| Administrator | Maintain platform quality | Manage users, categories and reported issues |

## 1.5 Project Scope

In Scope:

User registration, login, logout and profile management.

Income and expense transaction creation, editing, deletion and viewing.

Predefined and user-selectable expense categories.

Monthly budget creation and spending progress.

Dashboard showing balance, income, expenses and category summaries.

Transaction search, filtering and date-based viewing.

Budget alerts/notifications.

Basic monthly financial reports.

Administrator management of users and selected master data.

Responsive interface for desktop, tablet and mobile browsers.

Out of Scope for the first release:

Direct bank-account synchronization.

Credit-card payment processing.

Investment or stock portfolio management.

Loan approval or financial advisory services.

Native Android/iOS applications.

AI-generated financial advice.

# 2. Project Goals and Objectives

Provide one simple place to record and review personal income and expenses.

Help users understand their spending patterns through summaries and categories.

Allow users to set realistic monthly budgets and monitor progress.

Reduce manual spreadsheet work for basic personal expense tracking.

Protect personal financial records through authentication and authorization.

Deliver a clean responsive interface that can be learned with minimal guidance.

Build a maintainable MVP that can be expanded with future integrations.

## 2.1 Success Criteria

| Measure | Target |
| --- | --- |
| Transaction management | Users can add, edit, delete and view transactions successfully. |
| Budget monitoring | Users can create a monthly budget and see current utilization. |
| Dashboard | Income, expense, balance and category summaries are displayed correctly. |
| Performance | Common dashboard and transaction operations normally respond within 2 seconds under expected load. |
| Security | Passwords are securely hashed and protected routes enforce user permissions. |
| Usability | A new user can record an expense without formal training. |
| Quality | Critical workflows pass planned functional and integration testing before release. |

# 3. Requirements Analysis

## 3.1 Functional Requirements

| ID | Feature | Requirement |
| --- | --- | --- |
| FR-01 | Registration | The system shall allow a new user to create an account using required information. |
| FR-02 | Authentication | The system shall allow users to securely log in and log out. |
| FR-03 | Profile | Users shall be able to view and update basic profile information. |
| FR-04 | Add Transaction | Users shall be able to record income or expense with amount, date, category and description. |
| FR-05 | Edit Transaction | Users shall be able to modify their own transaction records. |
| FR-06 | Delete Transaction | Users shall be able to delete their own transaction records after confirmation. |
| FR-07 | Transaction History | Users shall be able to view their transactions in chronological order. |
| FR-08 | Categories | The system shall organize expenses using categories such as Food, Travel, Bills and Shopping. |
| FR-09 | Budget | Users shall be able to set a monthly spending budget. |
| FR-10 | Budget Alerts | The system shall notify users when spending reaches configured budget thresholds. |
| FR-11 | Dashboard | The system shall display income, expenses, balance and category-wise spending summaries. |
| FR-12 | Search & Filter | Users shall be able to search/filter transactions by category, date, type and amount. |
| FR-13 | Reports | Users shall be able to view a basic monthly spending report. |
| FR-14 | Admin | Administrators shall be able to manage users and selected system categories. |
| FR-15 | Validation | The system shall validate required fields and reject invalid amounts or dates. |

## 3.2 Non-Functional Requirements

| ID | Category | Requirement |
| --- | --- | --- |
| NFR-01 | Performance | Common pages/API requests should normally respond within 2 seconds under expected load. |
| NFR-02 | Availability | The planned production service should target at least 99% monthly availability. |
| NFR-03 | Security | Passwords must be hashed; authenticated requests must enforce authorization and input validation. |
| NFR-04 | Privacy | Users must only be able to access their own financial records unless an authorized admin function requires otherwise. |
| NFR-05 | Usability | Forms, labels, navigation and error messages should be clear to first-time users. |
| NFR-06 | Responsiveness | The interface should work on current desktop, tablet and mobile browsers. |
| NFR-07 | Maintainability | Code should use consistent structure, naming, comments and documentation where useful. |
| NFR-08 | Scalability | The architecture should allow additional users and features without a complete redesign. |
| NFR-09 | Backup | Important application data should be backed up according to the deployment plan. |
| NFR-10 | Accessibility | The interface should use semantic HTML, readable contrast, keyboard-friendly controls and descriptive labels. |

## 3.3 User Stories

As a user, I want to record an expense so that I know where my money is going.

As a user, I want to categorize expenses so that I can identify my major spending areas.

As a user, I want to set a monthly budget so that I can control my spending.

As a user, I want to see my remaining budget so that I know how much I can spend.

As a user, I want to filter transactions by date and category so that I can find specific records quickly.

As an administrator, I want to manage users and categories so that the platform remains organized.

# 4. High-Level System Workflow

A simplified user workflow for the MVP is:

| Step | User Action | System Response |
| --- | --- | --- |
| 1 | Register / Login | Validate credentials and open user dashboard. |
| 2 | Add income or expense | Validate data and save transaction. |
| 3 | Open dashboard | Calculate balance, totals and spending summary. |
| 4 | Set monthly budget | Save budget and calculate utilization. |
| 5 | Continue recording expenses | Update budget progress automatically. |
| 6 | Reach alert threshold | Display/send a budget notification. |
| 7 | Review report | Show monthly and category-based spending summary. |

## 4.1 Basic Data Entities

| Entity | Important Fields | Purpose |
| --- | --- | --- |
| User | user_id, name, email, password_hash, role | Account and authorization information. |
| Transaction | transaction_id, user_id, type, amount, category_id, date, description | Stores income/expense records. |
| Category | category_id, name, type, status | Organizes transactions. |
| Budget | budget_id, user_id, month, limit_amount | Stores monthly spending limits. |
| Notification | notification_id, user_id, message, type, read_status | Stores budget alerts and reminders. |

# 5. Risk Assessment

| ID | Risk | Probability | Impact | Mitigation Strategy |
| --- | --- | --- | --- | --- |
| R1 | Unclear requirements | High | Medium | Confirm requirements before development and review scope at milestones. |
| R2 | Scope creep | High | High | Focus on MVP features; keep additional ideas in a future-release backlog. |
| R3 | Financial data exposure | Medium | High | Use secure authentication, authorization, hashing, validation and HTTPS in deployment. |
| R4 | Incorrect calculations | Medium | High | Centralize balance/budget calculations and test boundary cases with known expected values. |
| R5 | Data loss | Medium | High | Use database backups and periodically test restoration procedures. |
| R6 | Schedule delays | Medium | High | Break work into milestones, track dependencies and prioritize critical features. |
| R7 | Poor usability | Medium | Medium | Perform basic usability testing and simplify confusing workflows. |
| R8 | Performance issues | Medium | Medium | Use pagination, indexes and efficient database queries; run basic load tests. |
| R9 | Unauthorized access | Medium | High | Apply role-based authorization and test protected routes with negative cases. |
| R10 | Deployment/configuration failure | Medium | Medium | Use environment variables, Git version control, staging checks and deployment documentation. |

## 5.1 Risk Management Approach

Risks will be reviewed at each milestone. High-impact security, privacy, authorization and calculation risks will be tested early because failures in these areas can directly affect user trust. Scope and schedule risks will be controlled by keeping the first release focused on core expense-tracking workflows.

# 6. Project Timeline and Milestones

The proposed project lifecycle is eight weeks. Week 1 is the planning and requirements phase; the remaining weeks cover design, implementation, testing and deployment.

| Week | Focus | Major Deliverables | Milestone |
| --- | --- | --- | --- |
| Week 1 | Planning & Analysis | Overview, requirements, risks, resources and milestones | Approved planning report |
| Week 2 | UI/UX & Architecture | Wireframes, database schema and API design | Approved design + architecture |
| Week 3 | Authentication & Setup | Project setup, database, registration/login and roles | Working authentication |
| Week 4 | Transactions | Income/expense CRUD, categories and history | Transaction module |
| Week 5 | Budget & Dashboard | Budgets, calculations, dashboard summaries | Budget + dashboard module |
| Week 6 | Reports & Notifications | Filters, monthly reports and budget alerts | Integrated feature set |
| Week 7 | Testing & Refinement | Functional, integration, security and usability testing | Test report + fixes |
| Week 8 | Deployment & Handover | Deployment, README, final demo and handover | Release candidate |

## 6.1 Week 1 Detailed Work Plan — 32 Hours

| Activity | Hours | Output |
| --- | --- | --- |
| Project understanding and problem definition | 3 | Define problem, target users, assumptions and scope. |
| Research and feature identification | 3 | Review common expense-tracking workflows and identify MVP features. |
| Goals and success criteria | 2 | Define project outcomes and measurable targets. |
| Functional requirements | 6 | Document user-facing features and system behavior. |
| Non-functional requirements | 4 | Define performance, security, privacy, usability and compatibility needs. |
| Risk assessment | 4 | Identify risks, probability, impact and mitigation. |
| Timeline and milestone planning | 3 | Create development roadmap and deliverables. |
| Resource and tool planning | 3 | Estimate roles, skills, tools and effort. |
| Documentation, proofreading and review | 4 | Format, check consistency and finalize submission. |

Total: 32 hours

# 7. Resource Planning

## 7.1 Human Resources

| Role | Key Skills | Estimated Hours | Engagement |
| --- | --- | --- | --- |
| Project / Business Analyst | Requirements, scope, documentation | 20 | Part-time |
| Frontend Developer | HTML, CSS, JavaScript, React or equivalent | 65 | Part-time |
| Backend Developer | REST APIs, authentication, business logic | 70 | Part-time |
| Database / DevOps Support | SQL, deployment, backups, CI | 30 | Part-time |
| UI/UX Support | Wireframes, responsive design, usability | 15 | Part-time |
| QA Tester | Functional, integration, usability and security testing | 35 | Part-time |

Estimated implementation effort: approximately 235 person-hours, excluding the 32-hour Week 1 planning assignment.

## 7.2 Tools and Technologies

| Area | Proposed Tool / Technology | Purpose |
| --- | --- | --- |
| Version Control | Git + GitHub | Source control, collaboration and project history |
| Frontend | HTML5, CSS3, JavaScript; React optional | Responsive user interface |
| Backend | Node.js + Express (proposed) | REST API and business logic |
| Database | PostgreSQL (proposed) | Persistent relational data |
| Design | Figma or equivalent | Wireframes and UI planning |
| API Testing | Postman or equivalent | API request and response testing |
| Project Tracking | GitHub Issues / Projects | Tasks, milestones and progress |
| Deployment | Vercel/Render/Railway or equivalent | Hosting and release |

## 7.3 Assumptions and Constraints

The project is hypothetical and intended to demonstrate professional planning.

The first release is an MVP and intentionally excludes bank integrations and payment processing.

The development team has basic computers, internet access and required software.

Actual production requirements would be refined with real stakeholders.

Financial data is sensitive, so production deployment would require stronger security review than this academic prototype.

# 8. Quality Assurance and Acceptance Approach

Requirements review: verify that every requirement is clear and testable.

Unit testing: test transaction and budget calculation logic with normal and edge-case values.

Functional testing: verify login, transaction CRUD, categories, budgets, dashboard and reports.

Authorization testing: verify users cannot access another user's financial records.

Negative testing: test invalid amounts, missing fields, invalid dates and unauthorized requests.

Usability testing: ask a small number of users to complete common tasks without training.

Regression testing: retest core features after major changes.

Release readiness: resolve all critical defects before final deployment.

## 8.1 Sample Acceptance Criteria

| Feature | Acceptance Criteria |
| --- | --- |
| Add Expense | Logged-in user enters valid amount/category/date, saves the transaction and sees it in history. |
| Edit/Delete | User can update or delete their own transaction and the dashboard totals update correctly. |
| Budget | User can set a monthly limit and see used and remaining budget. |
| Budget Alert | System displays an alert when configured spending threshold is reached. |
| Dashboard | Income, expense, balance and category summaries match stored transaction data. |
| Privacy | A user attempting to access another user's transaction receives an authorization failure. |

# 9. Project Deliverables

Week 1 project planning and requirements report.

UI wireframes and basic system architecture.

Database schema and API documentation.

Source code repository with meaningful commit history.

Working MVP web application.

Test cases and test results.

Deployment and setup documentation.

Final demonstration and handover notes.

# 10. GitHub Repository Plan

The GitHub repository will act as the central project workspace. It should contain source code, documentation, issues, and a README explaining how the project works.

README.md — project overview, features, setup instructions, screenshots and roadmap.

docs/ — requirements and project planning documents.

frontend/ — UI source code.

backend/ — API/server source code.

database/ — schema or migration files.

tests/ — test documentation and automated tests.

.gitignore — prevents secrets and generated files from being committed.

Suggested repository name: smart-expense-tracker. The final submission URL must use the intern's own GitHub username, for example: https://github.com/<your-username>/smart-expense-tracker

# 11. Public References

The following public resources are useful background references for requirements engineering, web development, security, accessibility and version control. The project plan itself is originally written for this internship exercise.

| Organization | Resource | Website |
| --- | --- | --- |
| OWASP Foundation | OWASP Top 10 — Web Application Security Risks | https://owasp.org/www-project-top-ten/ |
| MDN Web Docs | HTML, CSS and JavaScript documentation | https://developer.mozilla.org/ |
| W3C | Web standards and accessibility resources | https://www.w3.org/ |
| GitHub Docs | Repositories, Git and collaboration workflows | https://docs.github.com/ |
| IEEE Computer Society | Software engineering and requirements resources | https://www.computer.org/ |

# 12. Conclusion

Smart Expense Tracker is a focused and realistic software project for demonstrating the early stages of software development. The plan identifies a clear user problem, defines an MVP, documents functional and non-functional requirements, evaluates project risks, and establishes a practical timeline and resource plan.

The project should be developed incrementally, beginning with secure authentication and reliable transaction management before adding budgets, dashboards and reports. Particular attention should be given to privacy, authorization and calculation accuracy because the application handles personal financial information. Future versions could add bank integrations, recurring transactions, exports and advanced analytics after the MVP has been validated.

# Appendix A — Requirement Traceability Snapshot

| Requirement Area | Planned Module | Validation Method |
| --- | --- | --- |
| Authentication & roles | Auth module | Functional + security tests |
| Transactions | Transaction module | CRUD + calculation tests |
| Categories | Category module | Functional + validation tests |
| Budget | Budget module | Calculation + boundary tests |
| Dashboard | Dashboard module | Functional + data consistency tests |
| Reports | Reports module | Filter + data accuracy tests |
| Privacy | Application-wide | Authorization/negative tests |
| Performance | Application-wide | Basic performance/load checks |
| Accessibility | Frontend | Keyboard + semantic HTML review |